## Wedding Plan
WEDDING PLAN · UK DESTINATION
Based on EMBOK event management framework · Initiation → Planning → Implementation → The Event → Closure
📅 Wedding date | 2027-08-01 | You are in → | 🔍 Phase 1 · INITIATION
💰 Total budget | 20000 | 👥 Guest count | 45 | ← edit all blue cells freely
1 · INITIATION | 2 · PLANNING | 3 · IMPLEMENTATION | 4 · THE EVENT | 5 · CLOSURE
Now → Aug 26 | Aug 26 → Dec 26 | Dec 26 → Jun 27 | Jun 27 → Aug 27 | After Aug 27
▼ | ▼ | ▼ | ▼ | ▼
Phase | Task | Budget (£) | Done? | Notes
PHASE 1 · INITIATION
| Agree total budget & who is contributing |  |  | Family contributions? Couple paying? Get this locked first.
| Draft guest list (day + evening) |  |  | Guest count drives almost every other cost. Be ruthless early.
| Choose wedding date & season |  |  | Summer weekends cost more. Fri/off-peak = meaningful saving.
| Define style & vision |  |  | Mood board. Formal? Relaxed? Indoor? Outdoor? Rustic estate?
| Take out wedding insurance | 100 |  | Do this early. Covers cancellation, supplier failure, liability.
PHASE 2 · PLANNING
| Shortlist & visit venues (UK estate) |  |  | Venue = biggest cost + biggest constraint. Get 3+ quotes.
| Book venue + pay deposit | 5000 |  | Target: exclusive-use estate with on-site accommodation.
| Confirm guest accommodation at venue | 2500 |  | Block-book rooms. ~30 rooms × £80-120/night.
| Book registrar / marriage celebrant | 300 |  | Fixed statutory fee. Book as soon as venue is confirmed.
| Book photographer | 1400 |  | Books up 12–18 months out. Priority booking.
| Book videographer | 1000 |  | Optional but recommended. Highlight reel + full film.
| Book caterer & confirm F&B package | 4500 |  | ~£100/head for 45 guests. Confirm service charge inclusion.
| Book DJ or band | 800 |  | DJ ~40-50% cheaper than live band. Decide early.
| Send save-the-dates | 50 |  | Digital is free. Printed ~£1-2 each.
PHASE 3 · IMPLEMENTATION
| Order wedding dress | 1200 |  | Allow 4–6 months for delivery + alterations.
| Dress alterations | 150 |  | Not included in dress price. Budget separately.
| Groom & groomsmen attire | 500 |  | Suit hire ~£100-150/person. Buying from ~£200.
| Book hair & makeup artist (incl. trials) | 700 |  | Trial run ~£50-80 extra per person. Book early.
| Order wedding rings | 800 |  | Allow 6–8 weeks for custom. Don't leave this late.
| Book florist | 800 |  | Seasonal flowers = 20–40% cheaper. Reuse ceremony flowers.
| Venue décor & styling | 500 |  | Lighting, linen, centrepieces. Check what estate includes.
| Order wedding cake | 300 |  | 3-tier. Order 3 months out. DIY saves significantly.
| Send invitations & stationery | 200 |  | Invites + order of service + place cards + menus.
| Book guest transport (coaches/shuttles) | 400 |  | Airport or station pickups for destination guests.
| Plan welcome dinner (night before) | 600 |  | Destination staple. Informal dinner with arriving guests.
| Wedding favours | 90 |  | ~£2/guest. Edible favours most popular.
| Bridal transport | 400 |  | Vintage car hire ~£200-600. Or borrow a friend's.
| Confirm final seating plan |  |  | Do this 2-3 weeks before. Expect last-minute changes.
| Confirm all supplier schedules |  |  | Circulate a master timeline to every supplier.
PHASE 4 · THE EVENT
| Wedding rehearsal (day before) |  |  | Walk through ceremony. Confirm order of proceedings.
| Welcome dinner (evening before) |  |  | Budgeted above in Phase 3.
| The wedding day |  |  | You've planned it. Trust your suppliers. Enjoy it.
| Day-after brunch | 300 |  | Relaxed send-off with guests. Common for destination weddings.
PHASE 5 · CLOSURE
| Settle all outstanding supplier invoices |  |  | Final payments due within 7–14 days after the wedding.
| Return any hired items |  |  | Suits, décor props, equipment. Check hire contract dates.
| Send thank-you cards | 40 |  | Handwritten > printed. Do within 2 weeks.
| Register marriage certificate |  |  | Registrar handles this. Confirm timelines.
| Review & collect photos/video |  |  | Photographers typically deliver in 6–12 weeks.
| Post-event debrief — what worked, what didn't |  |  | Note learnings. You'll thank yourself later.
CONTINGENCY
| Contingency reserve (10% of budget) | 2000 |  | Do not spend unless needed. Industry standard 10–15%.
| TOTAL ESTIMATED | 24630 |  | 0/40 done
| REMAINING (vs budget) | -4630 |  | Update estimates above as you get real quotes
Blue cells = edit freely · Done? column: type Y when confirmed · Framework: EMBOK · Benchmarks: Bridebook UK 2026